## Projects
project_id | project_name | description | status | report_section | percent_complete | target_date | target_quarter | run_grow_transform | strategic_goal | project_type | milestones_completed
ITS-001 | 3rd District Flexpod Upgrade | Upgrade the 3rd District Flexpod to support Disaster Recovery Operations and 3rd District infrastructure | Not Started | Upcoming | 0 | 2027-09-30 | 2027 Q3 | Run | Cybersecurity and Resilience | Modernization or Upgrade
ITS-002 | Windows 11 Upgrade | Upgrading from Windows 10 to Windows 11 | In Progress | In Progress | 75 | 2026-12-31 | 2026 Q4 | Run | Workforce Modernization | Modernization or Upgrade
ITS-003 | 2016 Server Upgrades | Upgrading 2016 Servers across the environment. Evaluating Cloud migration vs on prem | In Progress | In Progress | 30 | 2027-06-30 | 2027 Q2 | Grow | Cybersecurity and Resilience | Modernization or Upgrade
ITS-004 | Video Surveillance Camera Program | 53 locations in the process of receiving new cameras or refreshed cameras | In Progress | In Progress | 45 | 2027-06-30 | 2027 Q2 | Run | Public Safety | Modernization or Upgrade
ITS-005 | PC Refresh | 5 year program to refresh percentage of General Fund PCs | In Progress | In Progress | 50 | 2027-06-30 | 2027 Q2 | Run | Workforce Modernization | Maintenance
ITS-006 | MFA compliance for the Division of Police | Implementing MFA for Police to meet CJIS/LEADS requirements | In Progress | In Progress | 5 | 2027-03-31 | 2027 Q1 | Grow | Public Safety | Compliance or Mandated
ITS-007 | Purview | Data security and governance solution for protecting and managing data | Not Started | Upcoming | 0 | 2027-06-30 | 2027 Q2 | Grow | Cybersecurity and Resilience | New Capability
ITS-008 | iPhone Refresh | Refresh to iPhone 17 | Paused | On Hold | 15 | 2026-12-31 | 2026 Q4 | Run | Workforce Modernization | Maintenance
ITS-009 | Cloud Contact Center Calling | Implementing Webex Cloud Contact Center Calling for CCA and Helpdesk | In Progress | In Progress | 33 | 2027-01-31 | 2027 Q1 | Transform | Resident Services | Modernization or Upgrade
ITS-010 | Halo | New Helpdesk/Service Desk System | In Progress | In Progress | 20 | 2027-01-31 | 2027 Q1 | Transform | Operational Efficiency | Modernization or Upgrade
ITS-011 | Accela | New Contractor Registration, Building and Zoning, Urban Forestry Permits, Right of Way/Obstruction permits, Rental Registration, Short Term Rental | In Progress | In Progress | 50 | 2027-03-31 | 2027 Q1 | Transform | Economic Development | New Capability
ITS-012 | ADA Website Compliance | PDF and Website compliance | In Progress | In Progress | 70 | 2027-01-31 | 2027 Q1 | Grow | Resident Services | Compliance or Mandated
ITS-013 | GovQA | Upgrade plus a demo of GovQA's AI redaction tool; Urban AI is now doing a requirements gathering for an RFP | Not Started | Upcoming | 0 | 2027-05-31 | 2027 Q2 | Grow | Resident Services | Modernization or Upgrade
ITS-014 | Matrix City Prosecutor's Office | Case management system for the City's Prosecutor's office that is integrated into the Courts Management System and Motorola P1 | In Progress | In Progress | 65 | 2026-12-31 | 2026 Q4 | Transform | Public Safety | New Capability
ITS-015 | Patient Care Reporting RFP | Division of EMS would like to go out for a RFP for the Electronic Patient Care Reporting System | Not Started | Upcoming | 0 | 2027-12-31 | 2027 Q4 | Grow | Public Safety | Modernization or Upgrade
ITS-016 | Police Led Intelligence RFP | RFP released for Gun Shot detection, License Plate Readers and Drone as a First Responder | In Progress | In Progress | 30 | 2026-12-29 | 2026 Q4 | Transform | Public Safety | New Capability
ITS-017 | IA Pro and Blueteam Upgrade | Upgrading from On Prem to Cloud version of IA Pro for OPS, Police, Fire, and EMS | In Progress | In Progress | 25 | 2027-01-31 | 2027 Q1 | Grow | Public Safety | Modernization or Upgrade | EMS migration completed
ITS-018 | Police Headquarters | Infrastructure setup for new Police HQ | In Progress | In Progress | 60 | 2026-12-31 | 2026 Q4 | Grow | Public Safety | New Capability
ITS-019 | T-Mobile Connectivity Project | Exploring Public Safety Vehicle connectivity with T-Mobile | In Progress | In Progress | 85 | 2026-10-31 | 2026 Q4 | Transform | Public Safety | Innovation or Pilot | Pilot nearing completion
ITS-020 | New CVD Data Center | Chagrin Valley Dispatch will be moving to a new Data Center | Not Started | Upcoming | 0 | 2027-01-31 | 2027 Q1 | Run | Public Safety | Modernization or Upgrade
ITS-021 | ATT Copper Line Replacement | Replacement of Copper Pots lines | In Progress | In Progress | 5 | 2027-04-30 | 2027 Q2 | Grow | Operational Efficiency | Compliance or Mandated
ITS-022 | SharePoint and File Migration Phase 1 | Migration of legacy files shares and setting SharePoint and team environments | In Progress | In Progress | 75 | 2027-02-28 | 2027 Q1 | Grow | Workforce Modernization | Modernization or Upgrade
ITS-023 | Smartsheet Refresher | Refresher for the internal PMs on Smartsheet | In Progress | In Progress | 40 | 2026-12-31 | 2026 Q4 | Run | Operational Efficiency | Maintenance
ITS-024 | Verint Shield Upgrade | Platform upgrade of 311 Verint system, currently in the development environment is available | In Progress | In Progress | 60 | 2027-03-31 | 2027 Q1 | Grow | Resident Services | Modernization or Upgrade
ITS-025 | Early Intervention Program | project team and PAT has made the decision to terminate the Benchmark Analytics project. Police turned over their leadership running the program several times, Benchmark was unable to deliver, their solution only reached a 79% confidence level | On Hold | On Hold | 79 |  |  | Transform | Public Safety | New Capability
ITS-026 | Firewall and switch replacements | Routine maintenance of replacing firewalls and switches, additional equipment will be ordered by the end of the year | Not Started | Upcoming | 0 | 2027-06-30 | 2027 Q2 | Run | Cybersecurity and Resilience | Maintenance
ITS-027 | Axon Officer Safety Bundle | Working with Public Safety to introduce new legislation this year for the Axon Officer Safety Bundle plan for project team equipment and evidence.com licenses | Not Started | Upcoming | 0 | 2026-12-31 | 2026 Q4 | Grow | Public Safety | New Capability
ITS-028 | Public Safety AI initiatives | Work with Renee, Tawanna and Atri for the development of CAD RMS chat bot. No one is using the SharePoint site, it has valuable information but its in a medium/format that the Division is not using; Also explore working with the respective Policy units to develop chat bots for Policies similar to the HR chat bot | Not Started | Upcoming | 0 | 2027-01-31 | 2027 Q1 | Transform | Public Safety | Innovation or Pilot